## Sheet1
Project Arrakis Scrum Sheet
Epic: Authentication & User Management
Task | Description | Story Points | Sprint | Type | Acceptance Criteria
Setup user login/signup API | Create POST /auth/login and POST /auth/signup endpoints | 5 | 1 | Backend | Users can sign up with email/username/password; login returns JWT token; 400 for invalid credentials; 201/200 for success.
JWT token issuance & middleware auth | Implement JWT generation and middleware to protect routes | 5 | 1 | Backend | All protected routes require valid JWT; 401 for invalid/expired tokens; middleware logs errors.
Get current user profile | Create GET /user/me endpoint to return user details | 3 | 1 | Backend | Returns user_id, username, email, role; 200 for success, 401 for unauthorized.
Role-based access control setup | Implement role-based permissions for book access | 5 | 2 | Backend | Users can only access their assigned books; admins can access all; 403 for unauthorized access.
Protected routing (auth guard) | Implement frontend auth guard for protected routes | 3 | 1 | Frontend | Unauthenticated users redirected to login; authenticated users access dashboard, search, books pages.
Navbar with user info + logout | Build navbar showing username and logout button | 3 | 1 | Frontend | Displays username; logout clears session and redirects to login; responsive design.
Epic: Dashboard Functionality
Task | Description | Story Points | Sprint | Type | Acceptance Criteria
API: Get upcoming trades (5 days) | Create GET /trades/upcoming?days=5 endpoint | 5 | 1 | Backend | Returns trades with settlement_date within next 5 business days; 200 for success; empty array for no results.
API: Get all open trades | Create GET /trades/open endpoint | 3 | 1 | Backend | Returns all trades with status "Open"; includes ISIN, CUSIP, issuer, counterparty; 200 for success.
API: Get previous trades (5 days) | Create GET /trades/previous?days=5 endpoint | 5 | 3 | Backend | Returns trades with settlement_date in past 5 business days; 200 for success; empty array for no results.
Trade status update API | Create PATCH /trades/:id/status endpoint | 5 | 3 | Backend | Updates trade status (e.g., Open to Closed); only permitted users can update; 200 for success, 403 for unauthorized.
Trade details API | Create GET /trades/:id endpoint | 3 | 3 | Backend | Returns trade details (book, security, counterparty, etc.); 200 for success, 404 for invalid ID.
Component: Upcoming trades | Build table for upcoming trades (5 rows) | 3 | 1 | Frontend | Displays 5 upcoming trades with ISIN, issuer, counterparty, maturity date; paginated if >5; fetches from API.
Component: All open trades | Build expandable list/table for open trades | 5 | 1 | Frontend | Shows all open trades; expandable rows show details; fetches from API; sortable by maturity date.
Component: Previous trades | Build table for previous trades (5 rows) | 3 | 3 | Frontend | Displays 5 past trades; paginated if >5; fetches from API; shows status color indicators.
Fetch & render API data | Integrate dashboard APIs into frontend | 5 | 1 | Frontend | Dashboard fetches and displays upcoming/open trades; updates on refresh; handles empty states.
Empty state UI | Design UI for no data in dashboard tables | 2 | 1 | Frontend | Shows "No trades found" message for empty results; user-friendly design.
Loader/spinner while fetching | Add loading indicators for dashboard | 2 | 1 | Frontend | Shows spinner during API calls; disappears when data loads or errors.
Status color indicators | Add color coding for trade status | 2 | 3 | Frontend | Green for Open, Red for Failed, Gray for Closed; consistent across tables.
Dashboard API integration | Connect dashboard components to backend APIs | 3 | 1 | Frontend | All dashboard components fetch and display data correctly; handle 4xx/5xx errors with toasts.
Epic: Search Functionality
Task | Description | Story Points | Sprint | Type | Acceptance Criteria
API: Search trades by ISIN, client name, book | Create GET /trades/search?q= endpoint | 5 | 2 | Backend | Searches trades by ISIN, issuer, counterparty, book; returns matching results; 200 for success.
Advanced filter API | Create GET /trades/filter for date, status, type | 5 | 4 | Backend | Filters trades by maturity date, status, asset type; supports AND/OR logic; 200 for success.
Autocomplete API for clients/books | Create GET /autocomplete endpoint | 3 | 4 | Backend | Returns suggestions for client names, books based on input; 200 for success; max 10 results.
Search bar with debounce + typeahead | Build search bar with debounced input and typeahead | 5 | 2 | Frontend | Debounces input (500ms); shows typeahead suggestions; submits on enter; responsive.
Table/grid for search results | Display search results in table/grid | 3 | 2 | Frontend | Shows ISIN, issuer, counterparty, maturity date; sortable columns; paginated.
Filters (dropdowns: status, date, asset type) | Add filter dropdowns for search page | 3 | 4 | Frontend | Dropdowns for status, date range, asset type; updates results dynamically; resets filters.
Highlighting matched keywords | Highlight search terms in results | 2 | 4 | Frontend | Matched keywords bolded/underlined in results; case-insensitive.
Search pagination | Add pagination to search results | 3 | 2 | Frontend | Shows 10 results per page; prev/next buttons; updates on filter change.
Error handling (no results, API failure) | Handle search errors in UI | 2 | 2 | Frontend | Shows "No results" for empty searches; toast for API errors (4xx/5xx).
Search API integration | Connect search page to backend APIs | 3 | 2 | Frontend | Search bar and filters fetch data correctly; handles errors with toasts.
Epic: My Books Functionality
Task | Description | Story Points | Sprint | Type | Acceptance Criteria
API: Get list of books assigned to user | Create GET /books endpoint | 3 | 2 | Backend | Returns user’s assigned books; includes book_id, name; 200 for success.
API: Book detail | Create GET /books/:id endpoint | 3 | 3 | Backend | Returns book details and associated trades; 200 for success, 404 for invalid ID.
API: Create/update trade note for a book | Create POST /books/:id/note endpoint | 3 | 3 | Backend | Adds/updates note for a book; 201/200 for success; 403 for unauthorized.
Books list view | Build UI for user’s books (cards/list) | 3 | 2 | Frontend | Displays user’s books; clickable to view details; responsive design.
Book details modal/view | Build modal for book details | 5 | 3 | Frontend | Shows book name, trades, notes; fetches from API; closeable modal.
Add/Edit Notes UI | Build UI for adding/editing book notes | 3 | 3 | Frontend | Textarea for notes; save/cancel buttons; saves via API; shows success toast.
Book-wise trade history table | Build table for book’s trade history | 3 | 3 | Frontend | Shows trades for a book; includes ISIN, status, maturity date; sortable.
My Books API integration | Connect books page to backend APIs | 3 | 2 | Frontend | Books list and details fetch data correctly; handles errors with toasts.
Epic: Integration & Infrastructure
Task | Description | Story Points | Sprint | Type | Acceptance Criteria
API Gateway / routing setup | Setup Express routing for all APIs | 5 | 1 | Backend | All API endpoints routed correctly; handles CORS; 404 for invalid routes.
Error handling & 404 response structuring | Implement global error handling | 3 | 1 | Backend | Returns structured 404/500 responses; logs errors to console.
Error logging API | Create POST /logs endpoint | 3 | 4 | Backend | Logs errors with timestamp, user_id, message; 201 for success.
Database schema creation | Create PostgreSQL schema for entities | 8 | 1 | Backend | Tables for Users, Books, Securities, Trades, Counterparties, book_user; enforces relationships.
Data seeding script for mock trades | Create script to seed sample data | 3 | 1 | Backend | Seeds 10+ trades, 5 books, 3 users, 5 counterparties; matches sample data format.
Swagger API documentation | Generate Swagger docs for APIs | 3 | 4 | Backend | Documents all endpoints, parameters, responses; accessible at /docs.
Side panel layout | Build side panel with 3 routes | 5 | 1 | Frontend | Sidebar with Dashboard, Search, My Books; highlights active route; responsive.
Toasts for success/error | Implement toast notifications | 3 | 2 | Frontend | Shows success/error messages for API calls; auto-dismiss after 3s.
Handle unauthorized access | Redirect on 401 errors | 2 | 2 | Frontend | Redirects to login on 401; shows error toast.
Mobile responsiveness tweaks | Ensure UI is mobile-friendly | 5 | 4 | Frontend | All pages (dashboard, search, books) render correctly on mobile; no overflow.
Unit test basic UI components | Write unit tests for key components | 5 | 4 | Testing | Tests for search bar, trade table, book list; 80% coverage; all pass.
E2E test for routing/navigation | Write E2E tests for app navigation | 5 | 4 | Testing | Tests login, dashboard, search, books routes; verifies redirects; all pass.